## Slide 1: Directions for this Template
Use the Slide Master to make universal changes to the presentation, including inserting your organization’s logo
  “View” tab > “Slide Master”
Replace placeholders (indicated by brackets [ ]) with information specific to your exercise
Delete any slides that are not relevant for your meeting
Font size should not be smaller than 22pt
Rev. April 2013
HSEEP-DD02
Notes: Organizations can modify and augment this presentation as needed.

## Slide 2: Exercise Name
Initial Planning Meeting
[Date]

## Slide 3: Welcome
[Name]
[Title (e.g., Exercise Director or Lead Planner)]
[Organization]
Notes: Organizations can modify and augment this presentation as needed.

## Slide 4: Administrative Remarks
Safety and emergency information
Restrooms
Cell phone etiquette
Breaks and lunch
Microphones (if applicable)

## Slide 5: Introductions
Name
Organization

## Slide 6: Trusted Agents
Trusted agents are the individuals on the Exercise Planning Team(s) who are trusted not to reveal exercise and scenario details to players or third parties before exercise conduct.
Trusted agents also develop pre-exercise materials, conduct exercise briefings, and support training sessions.
Information in this document is intended for the exclusive use of the exercise planners and is not to be released to the public or other personnel who do not have a valid need-to-know without prior approval from an authorized sponsor organization representative.
This document is not releasable to any public website.

## Slide 7: Agenda
[Time] Welcome and introductions
[Time] Planning updates
[Time] Exercise design
[Time] Exercise development
[Time] Action items and next steps

## Slide 8: Meeting Objectives
Review planning updates
Determine exercise design elements
Discuss exercise development items
Address outstanding issues
Discuss next steps and assign tasks

## Slide 9: Planning Updates
[Outcomes of the Concept and Objectives Meeting]
[Additional updates]
Notes: Populate this slide with any decisions made at the Concepts and Objectives Meeting, as well as any progress made between that meeting and the IPM.

## Slide 10: Exercise Design Discussion Points
Develop exercise objectives and align to core capabilities
Outline evaluation requirements
Identify relevant plans, policies, and procedures to be tested
Begin development of the exercise scenario
Identify modeling and simulation needs
Identify participating organizations and their extent of play
Identify needed exercise documentation
Highlight any local issues, concerns, or sensitivities

## Slide 11: Exercise Scope and Mission Area(s)
Exercise scope
  Exercise type
  Participation level
  Exercise duration
  Exercise location
  Exercise parameters
Mission area(s)
  [Prevention, protection, mitigation, response, recovery]
Notes: Determining exercise scope enables planners to “right-size” an exercise to meet the objectives while staying within the resource and personnel constraints of the exercising organizations. Key elements in defining exercise scope include exercise type, participation level, exercise duration, exercise location, and exercise parameters.
Exercise type may be seminar, workshop, tabletop, game, drill, functional, or full-scale.
Participation level refers to the organizations and level of personnel (e.g., tactical operators, line supervisors, agency directors) participating in the exercise, as well as the general number of personnel who will participate in the exercise.
Exercise duration should take into account how long it will take to address exercise objectives effectively, as well as resource constraints.
Exercise parameters outline what should be included in an exercise based on the objectives and scope, and what should not be exercised.

## Slide 12: Proposed Exercise Objectives
[Insert proposed objectives]
Notes: Exercise objectives are the distinct outcomes an organization wishes to achieve during an exercise. Objectives should align to the program priorities listed in the organization’s Multiyear Training and Exercise Plan, and take into account guidance from elected and appointed officials.
Exercise objectives are written as SMART objectives (specific, measurable, achievable, relevant, and time-bound)

## Slide 13: Aligned Core Capabilities
Objective 1: [Proposed Objective]
  Aligns to: [Core Capabilities (ex: Intelligence and Information Sharing)]
Objective 2: [Proposed Objective]
  Aligns to: [Core Capabilities (ex: Interdiction and Disruption, Physical Protective Measures)]
Objective 3: [Proposed Objective]
  Aligns to: [Core Capabilities (ex: Situational Assessment)]
Notes: Core capabilities are the distinct critical elements necessary to achieve the specific mission areas of prevention, protection, mitigation, response, and recovery. The exercise planning team aligns each exercise objective to one or more core capabilities.

## Slide 14: Evaluation Requirements
Capability targets are the performance thresholds for each core capability
  Targets are quantitative or qualitative
Critical tasks are the distinct elements required to perform a core capability
Exercise Evaluation Guides (EEGs) document exercise objectives, core capabilities, capability targets, and critical tasks
Notes: Evaluation requirements clearly articulate what will be evaluated during the exercise and how exercise play will be assessed. This information is documented in the Exercise Evaluation Guides (EEGs).
Capability targets are the performance thresholds for each core capability; they state the amount of capability that exercise players aim to achieve. Targets should be measurable, e.g., open 5 shelters within 3 hours of the incident. Generally, these targets are based on targets identified as part of an organization’s or jurisdiction’s THIRA or other threat and hazard identification or risk assessment process.
Critical tasks are distinct elements required to perform a core capability, e.g., implement MOU with shelters to handle pets. Critical tasks are derived from organizational plans or Standard Operating Procedures (SOPs), or discipline-specific standards.
Each participating organization identifies capability targets and critical tasks that are specific to their plans and procedures.

## Slide 15: Plans, Policies, and Procedures
[Relevant plans, policies, and procedures to be tested or examined during the exercise]
Notes: The exercise planning team identifies plans, policies, and procedures to be tested during the exercise. For each document, the planning team should also identify the owner or source of the document. These documents should be made available to the planning team as reference material to assist in developing evaluation requirements, the exercise scenario, or other exercise documentation.

## Slide 16: Scenario
The scenarios enables an exercise to assess objectives and core capabilities
Threat or hazard: [Proposed threat/hazard]
Conditions: [Scenario details such as locations, time, weather, etc.]
Modeling and simulation: [Any models or simulations to be used]
  Human-based
  Computer-based
Notes: A scenario is an outline or model of the simulated sequence of events for the exercise. It can be written as a narrative or depicted by an event timeline. The scenario should be realistic, plausible, and challenging, but not so complicated that it overwhelms players.
The exercise planning team should choose a threat or hazard that best assesses the exercise objectives and core capabilities. The identification of this threat or hazard scenario should also be based on the organization’s threat / hazard identification and risk assessment.
The exercise planning team should identify any models or simulations that could increase the realism of the scenario or bring cost savings to the exercise. Examples include human simulation provided though a Simulation Cell or mock media, or computer-based simulation such as wind damage or storm surge models.

## Slide 17: Exercise Participants
[List of participating organizations]
Notes: The planning team should identify all potential participating organizations, as well as the extent of play for each organization, or any factors that might limit an organization’s participation.

## Slide 18: Exercise Documentation
Identify required documentation:
Extent of Play Agreement (XPA)
EEGs
Situation Manual (SitMan)
Facilitator Guide
Exercise Plan (ExPlan)
Controller/Evaluator (C/E) Handbook
Master Scenario Events List (MSEL)
Multimedia Presentation
Participant Feedback Form
Notes: The exercise planning team should select the standard documentation appropriate for the exercise, and identify any additional required documentation.

## Slide 19: Local Issues and Concerns
[Any issues, concerns, or sensitivities for discussion and consideration]

## Slide 20: Exercise Development Discussion Points
Plan for exercise logistics
  Location
  Audio/visual (A/V) requirements
  Duration and schedule
Identify exercise staffing requirements
Outline exercise planning team roles and responsibilities
Develop exercise planning timeline

## Slide 21: Exercise Logistics
Exercise location
  [Location requirements, including seating capacity, layout, etc.]
  [Potential locations]
A/V requirements
  [A/V requirements, such as screens, microphones, etc.]
Exercise duration and schedule

## Slide 22: Exercise Staffing
Subject-Matter Experts (SMEs)
Exercise control
Exercise evaluation
Notes: The exercise planning team should identify staffing requirements for the exercise, including:
Subject-matter experts for scenario development or vetting,
Controllers, including functional area controllers and/or Simulation Cell controllers
Evaluators, including any needs for specific subject-matter expertise

## Slide 23: Exercise Planning Team
Roles and responsibilities
  [Planning team roles and assignments]
Communications
  [Preferred frequency and methods of communications]
Notes: The exercise planning team should make specific assignments for key roles such as Exercise Director, Exercise Planning Team Leader, Command Section, Operations Section, Planning Section, Logistics Section, and Administration/Finance Section.
The planning team should also establish its preferred frequency and methods of communications, such as biweekly teleconferences or status update emails.

## Slide 24: Exercise Planning Timeline
Midterm Planning Meeting: [Date and location]
  Milestones and deliverables before next meeting
MSEL Meeting [as needed]: [Date and location]
  Milestones and deliverables before next meeting
Final Planning Meeting: [Date and location]
  Milestones and deliverables before next meeting
Exercise: [Date and location]

## Slide 25: Outstanding Issues
[Any outstanding issues to address]
Notes: The planning team should address any outstanding issues or concerns that came up during the meeting.

## Slide 26: Action Items
Distribute IPM minutes: [Responsible organization/individual], [due date]
Draft exercise documentation
  EEGs: [Responsible organization/individual], [due date]
  [Other documents as needed]
[Additional action items]

## Slide 27: Next Meeting
[Date]
[Time]
[Location]